## VISTAS dev plan 2013-4
VISTAS Development Plan, November 2013 through September 2014
added (unless otherwise specified, added as a result of the VISTAS November Retreat) | priority | What | 11/15 list? | for whom | Start | 1st demo | final | deverloper responsible | Comment | Comment2 | Comment 3
|  | multiple scenes on same window, side by side |  | Bob, all |  |  | 2013-12-01 | Nik | Bob is already using this | should be function of software design
2013-12-06 |  | multiple data on same scene, overlapped | [6 empty] | need 2 data sets that fit together | has not been tried…in theory it works | distinguish from row3
|  | save projects across sessions |  | all | 2013-12-01 | 2014-01-01 | 2014-02-01 | Nik | to save user time and effort in setup for replaying visualizations
|  | save parameters across sessions | no | all | 2014-02-01 | 2014-03-01 | 2014-04-01 | Nik | will allow easy repeat of visualizations
| high | fly-through |  | John | 2013-03-01 | 2013-04-01 | ? | Vir, justin? | working now, but needs vetting by John/Patrick | done as a proof of concept, waiting on vistas as backend to envision….much of the polish is UI work - Justin?
| high | fly-through - edit the path to refine the flythrough |  | John | ? | ? | ? | Vir, justin?
| low | fly-through - play animation concurrently |  | John | ? | ? | ? | Vir, justin? | a fly through can be of static or dynamic (animation) visualization; let the user control speed of animation during a flythrough
|  | 2D graphs |  | Bob | 2013-08-01 | 2013-11-01 | ? | Nik | improvements still needed
|  | 2D - map any fields to X/Y |  | all | 2014-01-01 | 2014-02-01 | 2014-05-01 | Nik |  |  | would be nice to have prior to extrusion
|  | 2D- dynamic bar charts |  | Bob | 2014-03-01 | 2014-05-01 | 2014-07-01 | Nik | how will user specifies data to go on bars
|  | stats - min, max | no | Nik | n/a |  |  | Nik | exists currently | need mechanism to view easily
| ? | stats - cumulative | no | Nik | n/a |  |  | Nik | side effect of dynamic bar charts | need mechanism to view easily
|  | UI - friendlier |  | all | 2014-02-01 | 2014-04-01 | 2014-06-01 | Justin | UI is functional, but difficult to navigate | consult w/ Margaret Burnett January ?
|  | UI - better user documentation |  | all | 2013-12-01 | 2014-02-01 | 2014-06-01 | Justin | current documentation OK for setup | no documentation beyond setup
|  | Movies - Generate MPEG4 files |  | all | 2014-01-01 | 2014-02-01 | 2014-03-01 | Nik | for data animation and fly-through
|  | VISTAS as ENVISION back-end |  | John | 2013-05-01 | ? | 2014-03-01 | Vir | need dev. collaboration from Patrick, in John's group - mods to ENVISION
|  | VISTAS as VELMA back-end |  | Bob | ? | ? | ? | ? | hold til all VELMA functionality and ENVISION back-end ok
|  | Enhanced use of color | [5 empty] | Dani | opacity, desaturation | uncertainty as desaturation; how can user specify confidence level? Normalized 0-100?
|  | 5D Visualization |  | all | 2014-09-01 | ? | ? | ? | XY on ground, contours, height, color | map any data field to contours, height, or color
|  | Data Extrusion (time) |  | all | 2014-03-01 | 2014-05-01 | 2014-08-01 | Dani, then Nik to finalize | time as Z,; other two (usually xy) stacked as or other | explore change points w/ 3D; mark and explore on other maps
|  | Visualization Annotation |  | all | 2014-03-01 | 2014-04-01 | 2014-08-01 | Justin, Dani, then Nik to finalize | text boxes, 3D arrows from box to location in 3D terrain | clickable to view on any scene
VISTAS 2013-14 Prototypes - but not integrated with VISTAS in this year
|  | 3D flow vis1 (webGL) |  | Christoph | 2014-11-01 | 2014-03-01 | 2014-05-01 | Kendra | prototype for point cloud wind vis | if successful, wanted, will integrate FWS 2014-5
|  | 3D flow vis1 (OpenGL) |  | Christoph | 2014-11-01 | Jan-2014? | 2014-05-01 | Vir | prototype for mesh cloud wind vis | if successful, wanted, will integrate FWS 2014-5 | 3D line integral convolution, Vir's master's project
|  | Stereographics (OpenGL) |  | all | ? | ? | ? | Mike | prototype for enhanced VISTAS | if successful, wanted, will integrate in VISTAS
Additional development implicated by above development
|  | VISTAS fileshare (for large files) | no | bob, john | 2014-01-01 | 2014-02-01 |  | Judy, Mike | given large size of VISTAS' users' data, need commonly accessible fileshare |  | MS Azure? Google? Amazon?
|  | terabyte data capacity | no | bob, john | ? | ? | ? | Vir, Nik, Mike | in principle, VISTAS will do this, but we won't know for sure until we test it; still involves downloading large data sets |  | need larger data sets, for that need fileshare
|  | Performance enhancements |  | all | ongoing | ongoing | ongoing | Nik, Vir, Mike | VISTAS is slow for some operatoiins
Desirable Features requested by Collaborators, but currently out of scope
|  | What |  | for whom | Start | 1st demo | final | deverloper responsible | Comment | Comment2 | Comment 3
|  | Video editing |  | all | -- | -- | -- | Dani? | excellent packages exist; | Dani has expertise to demo VISTAS animation editing to collaborators
|  | Statistics |  | Bob? | -- | -- | -- | future | R could be attached as VISTAS plug in, but no VISTAS personnel time for this; we could help Allen do it?
|  | Networks (next proposal?) |  | John | -- | -- | -- | future | now cover 3 science data types (points, shapes, now vectors) | existing network vis show topology NOT magnitude, speed | research for future proposal?
|  | Lidar |  | Bob, John? | -- | -- | -- |  | consider collaboration with Spies et al LiDAR work at HJA |  | research for future proposal?
|  | photorealism | no | John, Bob? | -- | -- | -- |  | now allow textures |  | research for future proposal?